## A-22 A (14 S)
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: A-22 A (2/1-14 S) |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on pressure tested mechanical plug | Yes | Yes | Yes | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping required | Yes | Yes | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | No | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | No | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug (if parameteres above have all stated yes as accepted, Repsol does not require tagging) |  | No | Yes | No
Cement plug tagged |  | No | Yes, cement dressed of down to 4016 m and P. tested to 160 bar with 1,6 sg WBM | Yes, tagged at 167 m
Comments |  | Primary reservoir barrier allready set when temporary plugging the exploration well in 2009. The secondary reservoir barrier is combined with the primary Forties barrier | Cement plug set in 2009 from OH into 9 5/8" csg shoe was leaking. This plug was dressed of down to 4931 m and used as the base for the new cement plugs (3 x 250 m plugs and 1 x 154 m cmt plugs set "wet in wet") together with formation test assy. With swab cups. | 100 m cement plug set on top of pressure tested EZSV.

## A-20
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: A-20 |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on tagged and pressure tested mechanical plug | Yes | Yes | Yes* | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping requiered | Yes | Yes | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | No | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug | Yes / No | No | No | No
Cement plug tagged | Yes / No | No* | Yes* | Yes, tagged at 165 m
Comments |  |  | *Reservoir and Forties barriers set wet in wet. 3 x 210 m cement plugs. Uppermost plug tagged and dressed off until firm cement. Well A-20 was 2nd phase II well - strategy in main program is to tag the cement plugs in the 3 first wells.

## A-08 A
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: 2/1-A-8 A |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on pressure tested mechanical plug | Yes | Yes | Yes | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping required | Yes | Minor water volume observed Pulling out of first cmt plug. Plugs 2-6 dry | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | Yes | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug (if parameteres above have all stated yes as accepted, Repsol does not require tagging) |  | NO | NO | NO
Cement plug tagged |  | 6 plugs set wet-in-wet, tagged last plug. | Yes, cement dressed of down to 2545 m MD and tagged with 10MT. | Yes, tagged at 198 m
Comments |  | project requirement to tag first 3 wells | project requirement to tag first 3 wells

## A-04
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: A-04 |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on tagged and pressure tested mechanical plug | Yes | Yes | Yes | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping requiered | Yes | Yes | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | No | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug | Yes / No | No | No | No
Cement plug tagged | Yes / No | No | No | Yes, tagged at 232 m
Comments |  | Reservoir and Forties barriers consists of 4 x 250 m cement plugs set "wet in wet" from 3800 - 2800 m. Base of cement was EZSV at 3800 m. | One of the transition plugs (3300 - 3050 m) was slightly wet when POOH, but no barriers required to be covered by this interval - mainly influx zone and linerlap in this interval. | 9 5/8" csg perforated & 200m cement pumped into the 9 5/8" x 13 3/8" annulus. 175 m cement barrier set on top of Spartan plug inside 9 5/8" csg

## A-12
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: A-12 |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on tagged and pressure tested mechanical plug | Yes | Yes | Yes* | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping requiered | Yes | Yes | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | No | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug | Yes / No | No | No | No
Cement plug tagged | Yes / No | No | No | Yes, tagged at 170 m
Comments |  |  | *Reservoir and Forties barriers set wet in wet. 3 x 250 m cement plugs.

## A-28 A
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: A-28 A |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on pressure tested mechanical plug | Yes | Yes* | Yes | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping required | Yes | Yes | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | No | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug (if parameteres above have all stated yes as accepted, Repsol does not require tagging) | Yes / No | No | No | No
Cement plug tagged | Yes / No | No | No | Cement plug tagged offline at 167 m
Comments |  | Production packer and mechanical plug installed in phase 1 used as foundation for the reservoir barrier as it was not possible to pass oval csg at 3302 m with the 7" EZSV. 10 m from top of tubing cut and down to the production packer (ie a volume of 85 liters).

## A-32 D
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: A-32 D |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on pressure tested mechanical plug | Yes | Yes | Yes | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping required | Yes | Yes | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | No | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug (if parameteres above have all stated yes as accepted, Repsol does not require tagging) | Yes / No | Yes | No | No
Cement plug tagged | Yes / No | Yes, TOC tagged at 3616 mMD with 8 tons. | Yes, TOC tagged at 3616 mMD with 8 tons. | Yes, tagged at 304 m
Comments |  | 2 x 250 m reservoir and Forties barriers set "wet in wet" from 4098 - 3598 m. First plug set on top of pressure tested EZSV. Sele / Forties / Lista sands Inflow Zone: 3864 - 4015 mMD RKB | *2 x 250 m reservoir and Forties barriers set "wet in wet" from 4098 - 3598 m. First plug set on top of pressure tested EZSV. Sele / Forties / Lista sands Inflow Zone: 3864 - 4015 mMD RKB | 13 3/8" csg perforated & 200 m cement pumped into the 13 3/8" x 18 5/8" annulus. 100 m cement barrier set on top of Spartan plug inside 13 3/8" csg

## A-07 AT2
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: A-07 AT2 |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on tagged and pressure tested mechanical plug | Yes | Yes* | Yes | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping requiered | Yes | Yes | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | No | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug | Yes / No | No | No | No
Cement plug tagged | Yes / No | No | No | Yes, tagged at 217 m
Comments |  | * Reservoir barriers set on ME plug installed in Phase I, pressure tested, not tagged. (No EZSV run on the cement stinger).

## A-03
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: 2/1-A-3 |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on pressure tested mechanical plug | Yes | Yes | Yes | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | ? | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping required | Yes | N/A (CT) | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | N/A | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | NO | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug (if parameteres above have all stated yes as accepted, Repsol does not require tagging) |  | yes | NO | No
Cement plug tagged |  | YES (CT-2009) | NO | Yes, tagged at 213 m
Comments |  | Primary reservoir barrier already set in 2009.

## A-06 A
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: A-06 A |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on tagged and pressure tested mechanical plug | Yes | Yes | Yes | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping requiered | Yes | Yes | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | Yes | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug | Yes / No | No | No | No
Cement plug tagged | Yes / No | Yes, tagged (5MT) at 3980 mMD with Tormation test BHA | No | Yes, tagged at 316 m
Comments |  | Cement barrier No.1 (reservoir barrier) set from 4236mMD to 3980mMD. Set on top of pressuretested EZSV | 4 x 260 m cement barriers set ‘’wet in wet’’ from top of the swabcups on the Formation test BHA from 3910 -2870 mMD RKB. | 9 5/8" csg perforated & 200m cement pumped into the 9 5/8" x 13 3/8" annulus. 175 m cement barrier set on top of Spartan plug inside 9 5/8" csg

## A-17 A
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: A-17 A |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on pressure tested mechanical plug | Yes | Yes | Yes* | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping required | Yes | Yes | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | No | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug (if parameteres above have all stated yes as accepted, Repsol does not require tagging) | Yes / No | No | No | No
Cement plug tagged | Yes / No | No | No | Yes
Comments |  | 5 x 250 m cement plugs set wet-in-wet from 4250 - 3000 mMD. Set on top of pressure tested EZSV | *5 x 250 m cement plugs set wet-in-wet from 4250 - 3000 mMD. First plug set on top of pressure tested EZSV. | 100 m cement plug set on top of pressure tested EZSV. Cement plug tagged offline at 147 m (note - tagged shallow due to pulling 1 stand too much prior to circulation )

## A-29
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: A-29 |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on pressure tested mechanical plug | Yes | Yes | Yes* | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping required | Yes | Yes | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | Yes | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug (if parameteres above have all stated yes as accepted, Repsol does not require tagging) | Yes / No | No | No | No
Cement plug tagged | Yes / No | No | No | Yes
Comments |  | 4 x 250 m cement plugs set wet-in-wet from 5617 - 4617 mMD. First plug set on top of pressure tested EZSV. | *4 x 250 m cement plugs set wet-in-wet from 5617 - 4617 mMD. First plug set on top of pressure tested EZSV. Sele / Forties / Lista sands Inflow Zone: 4986 - 5079 mMD RKB | Cement plug tagged offline at 162 m

## A-25 A
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: A-25 A |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on pressure tested mechanical plug | Yes | Yes | Yes* | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping required | Yes | Yes | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | Yes | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug (if parameteres above have all stated yes as accepted, Repsol does not require tagging) | Yes / No | No | No | No
Cement plug tagged | Yes / No | No | No | Yes
Comments |  | 4 x 250 m cement plugs set wet-in-wet from 4402 - 3402 mMD. First plug set on top of pressure tested EZSV | * 4 x 250 m cement plugs set wet-in-wet from 4402 - 3402 mMD. First plug set on top of pressure tested EZSV Sele / Forties / Lista sands Inflow Zone: 3965 - 4132 mMD RKB | 13 3/8" csg perforated & 200m cement pumped into the 13 3/8" x 18 5/8" annulus. 100 m cement barrier set on top of Spartan plug inside 13 3/8" csg Cement plug tagged offline at 286 m

## A-30 AT2
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: A-30 AT2 |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on pressure tested mechanical plug | Yes | Yes | Yes* | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping required | Yes | no | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | Yes | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug (if parameteres above have all stated yes as accepted, Repsol does not require tagging) | Yes / No | YES | No | No
Cement plug tagged | Yes / No | YES | No | Yes
Comments |  | 2 x 250 m cement plugs set wet-in-wet from 4845-5345 mMD. First plug set on top of pressure tested EZSV. Tagged | * 4 x 250 m cement plugs set wet-in-wet from 4402 - 3402 mMD. First plug set on top of pressure tested EZSV Sele / Forties / Lista sands Inflow Zone: 3965 - 4132 mMD RKB | Cement plug tagged offline at 163 m

## A-31 AT2
Gyda P&A Cement Job Performance Matrix
This Checklist will be used to verify cement plugs placed in cased-hole without the requirement to perform a physical tag of TOC.
Well: A-31 AT2 |  | Reservoir Well Barrier | Forties Well Barrier | Open Hole To Surface Barrier
Parameters | Requirement | Achieved | Achieved | Achieved
Well is static pre-job (Flowcheck) | Yes | Yes | Yes | Yes
Cement plug set on pressure tested mechanical plug | Yes | Yes | Yes | Yes
No losses seen in pre-job circulation or during the execution. | Yes | Yes | Yes | Yes
Additive usage as per Halliburton Program | Yes | Yes | Yes | Yes
No mixing problems / density variations during the job affecting the cement plug quality | Yes | Yes | Yes | Yes
Volumes and Rates as per ITD – no pump shutdowns during displacement of cement | Yes | Yes | Yes | Yes
Pulling dry pipe out of cement. No additional pumping required | Yes | Yes | Yes | Yes
Cement in return at surface when circulating at TOC | Yes | Yes | Yes | Yes
Firm cement in surface samples / UCA cell | Yes | Yes | Yes | Yes
≥200m cement plug set in cased hole for reservoir & Forties barriers | Yes | Yes | Yes | N/A
≥100m cement plug set in cased hole for Open Hole To Surface Barrier | Yes | N/A | N/A | Yes
Well is static post-job (no more than thermal effects observed) | Yes | Yes | Yes | Yes
≤70° inclination in cement barrier placement interval. | Yes | Yes | Yes | Yes
Required to tag cement plug (if parameteres above have all stated yes as accepted, Repsol does not require tagging) | Yes / No | No | No | No
Cement plug tagged | Yes / No | No | No | Yes
Comments |  | 2 x 250 m cement plugs set wet-in-wet from 5380 - 4880 mMD. First plug set on top of pressure tested EZSV | 2 x 250 m cement plugs set wet-in-wet from 3660 - 3160 mMD. First plug set on top of pressure tested EZSV Sele / Forties / Lista sands Inflow Zone: 3660 - 3857 mMD RKB | 100 m cement plug set on top of pressure tested EZSV. Cement plug tagged offline at 286 m